## Sheet2
Owner | Sum of Effort_Var_h
Arch | 18
DE 1 | 26
DE 2 | 30
Dev A | 19
Dev B | 12
PM | 8
UX | 6
Grand Total | 119

## Sheet1
WBS_ID | Task_Name | Owner | Baseline_Start | Baseline_Finish | Baseline_Effort_hrs | Predecessor(s) | Actual_Start | Actual_Finish | Actual_Effort_hrs | %_Complete | Effort_Var_h | Status_RAG
1 | Initiation & Planning | PM | 2024-04-01 | 2024-04-05 | 40 |  | 2024-04-01 | 2024-04-05 | 42 | 100 | 2 | Amber
1.1 | Kick-off & charter | PM | 2024-04-01 | 2024-04-02 | 16 |  | 2024-04-01 | 2024-04-02 | 18 | 100 | 2 | Amber
1.2 | Stakeholder & risk register | PM | 2024-04-03 | 2024-04-05 | 24 | 1.1 | 2024-04-03 | 2024-04-05 | 24 | 100 | 0 | Green
2 | Architecture & Solution Design | Arch | 2024-04-08 | 2024-04-19 | 80 | 1 | 2024-04-08 | 2024-04-21 | 86 | 100 | 6 | Amber
2.1 | Tech stack & cloud landing zone | Arch | 2024-04-08 | 2024-04-12 | 40 | 1 | 2024-04-08 | 2024-04-13 | 44 | 100 | 4 | Amber
2.2 | Data model & security design | Arch | 2024-04-15 | 2024-04-19 | 40 | 2.1 | 2024-04-15 | 2024-04-21 | 42 | 100 | 2 | Amber
3 | Data-Pipeline Build | DE 1 | 2024-04-22 | 2024-05-17 | 120 | 2 | 2024-04-22 | 2024-05-20 | 128 | 100 | 8 | Amber
3.1 | Ingestion service (audio & docs) | DE 1 | 2024-04-22 | 2024-05-03 | 60 | 2.2 | 2024-04-22 | 2024-05-06 | 64 | 100 | 4 | Amber
3.2 | Datastore schema & indexing | DE 2 | 2024-05-06 | 2024-05-17 | 60 | 3.1 | 2024-05-07 | 2024-05-20 | 64 | 100 | 4 | Amber
4 | Model Integration & Tuning | DE 2 | 2024-05-20 | 2024-06-28 | 160 | 3 | 2024-05-21 | 2024-07-02 | 172 | 100 | 12 | Red
4.1 | Speech-to-text model integration | DE 2 | 2024-05-20 | 2024-06-07 | 80 | 3.2 | 2024-05-21 | 2024-06-10 | 88 | 100 | 8 | Amber
4.2 | Image OCR & tagging | DE 1 | 2024-06-12 | 2024-06-24 | 40 | 4.1 | 2024-06-12 | 2024-06-24 | 42 | 100 | 2 | Amber
4.3 | LLM prompt engineering & fine-tune | DE 2 | 2024-06-26 | 2024-07-02 | 40 | 4.2 | 2024-06-26 | 2024-07-02 | 42 | 100 | 2 | Amber
5 | Backend APIs | Dev A | 2024-06-03 | 2024-07-12 | 160 | 3 | 2024-06-03 | 2024-07-16 | 170 | 100 | 10 | Red
5.1 | CRUD & auth endpoints | Dev A | 2024-06-03 | 2024-06-14 | 80 | 3.2 | 2024-06-03 | 2024-06-18 | 84 | 100 | 4 | Amber
5.2 | AI processing orchestration API | Dev B | 2024-06-19 | 2024-07-16 | 80 | 5.1 | 2024-06-19 | 2024-07-16 | 86 | 100 | 6 | Amber
6 | Frontend & UX | UX | 2024-06-17 | 2024-08-02 | 120 | 5 | 2024-06-17 | 2024-08-06 | 126 | 100 | 6 | Amber
6.1 | Wire-frames & usability testing | UX | 2024-06-17 | 2024-06-30 | 40 | 5.1 | 2024-06-17 | 2024-06-30 | 42 | 100 | 2 | Amber
6.2 | React UI for Q&A & Smart Search | Dev B | 2024-07-03 | 2024-07-30 | 60 | 6.1 | 2024-07-03 | 2024-07-30 | 66 | 100 | 6 | Amber
6.3 | Report export & theming | UX | 2024-07-31 | 2024-08-06 | 20 | 6.2 | 2024-07-31 | 2024-08-06 | 18 | 100 | -2 | Green
7 | System Integration & Sprint 8 Hardening | Dev A | 2024-08-05 | 2024-08-16 | 80 | 4,5,6 | 2024-08-05 | 2024-08-20 | 85 | 100 | 5 | Amber
8 | Functional & Non-functional Testing | DE 1 | 2024-08-19 | 2024-09-13 | 120 | 7 | 2024-08-21 | 2024-09-18 | 128 | 100 | 8 | Amber
8.1 | Test case design & automation | DE 1 | 2024-08-21 | 2024-09-02 | 60 | 7 | 2024-08-21 | 2024-09-02 | 64 | 100 | 4 | Amber
8.2 | Performance & security testing | DE 2 | 2024-09-04 | 2024-09-18 | 60 | 8.1 | 2024-09-04 | 2024-09-18 | 64 | 100 | 4 | Amber
9 | User Acceptance (Sprint 12) | PM | 2024-09-17 | 2024-09-30 | 40 | 8 | 2024-09-17 | 2024-09-30 | 44 | 100 | 4 | Amber
10 | Deployment & Go-live | Arch | 2024-10-01 | 2024-10-07 | 40 | 9 | 2024-10-01 | 2024-10-07 | 46 | 100 | 6 | Amber
11 | Project Closure & Lessons Learned | PM | 2024-10-08 | 2024-10-11 | 32 | 10 | 2024-10-08 | 2024-10-11 | 32 | 100 | 0 | Green